## All activites
Action Log at July 2017
Line item | RAG rating | Priority /urgency | Strategic objective | Area | Area 2 | Action/comment | Comment/progress | Next action | Resp | Sub-grp sponsor
1 | G | 2. Medium | Support implementation | Publish guidelines and materials | Public and victims | via media: publicise release of draft and definitive guidelines and when guidelines come into force. | Ongoing work to nurture relationships with key journalists and identify specialist channels. | DGs: knives, breach, terrorism (Mar 18); Consultations: terrorism (Oct 17), public order (?Feb 18), arson (Feb 18) | NM | JillG
2 | G | 2. Medium | Support implementation | Publish guidelines and materials | Working with partners | via practitioners: Maintain focus on implementation of guidelines. Issue summary briefing on new definitive guidelines for each agency and notification of coming into force. | All agencies receive and distribute articles via appropriate channels. |  | NM | JillG
3 |  | 2. Medium | Support implementation | Publish guidelines and materials |  | Manage design, production, print and digital publication of published materials. | All publications available in print and digital formats by publication date. |  | GS | JillG
4 |  | 2. Medium | Reinforce reputation | Publish guidelines and materials |  | Ensure effective launches of definitive guidelines, and appropriate participation in consultations | Design plan to evaluate launch and publicity activities, particularly impact on consultation responses | Plan in place for next consultation: child cruelty (May¦) | PH/NM | MG
5 |  | 1. High | Support implementation | Digital capacity |  | Develop digital guidelines for Crown Court (CCSG) | Scope requirements. Draft project plan for agreement w SC SMT and C&C sub-grp. User research. Brief digital agency. | Circulate draft project plan. Contact Judge's Engagement Group and identify digital lead, if any. Identify potential advisory group. Sit in on Crown Court proceedings. | PH | JulianG/JillG
6 |  | 2. Medium | Support implementation | Digital capacity |  | Create digital environment for successful implementation of CCSG | Key players in eJudiciary and other digital projects across CJS identified, demos seen. Press for "tile" and integrated content on eJudiciary. | Revisit eJudiciary re presentation and access via Bench Solution. | PH | JulianG/JillG
7 |  | 1. High | Support implementation | Digital capacity |  | Refine MCSG in line with user feedback, and enhance functionality. | Digital agency briefed in line with existing feedback. Test with advisory and focus groups. Prep video "how to" guide. Comms for release of improvements and discontinuation of pdf. Next phase: user research, improve functionality, additional tools. | Launch due 21 Aug. Roll-out comms from 28July | PH | JillG
8 |  | 1. High | Support implementation | Digital capacity |  | Develop Welsh-language MCSG | Welsh Language Unit engaged. MOU to be drafted. Mirror website created. Lord Chief's office re evaluation panel. | Draft MOU. Chase Lord Chief's office. Contact stakeholders. | PH | JillG
9 | G | 3. Low | Support implementation | Digital capacity |  | Refine and develop website - see separate entry for Members' area. | Build basic review requirements into new contract. Review content, language, structure. | Analyse user feedback from ongoing survey to inform development. Plan further user research. | PH/GS | SB
10 | G | 3. Low | Support implementation | Digital capacity |  | Refine and develop Members' area of website, particularly tool for online collaboration on documents | Review requirements included in new contract. Survey Members. | Develop user research. Analyse existing and new user feedback to inform development. | PH/GS | JillG
11 |  | 2. Medium | Promote confidence | Digital capacity |  | Make creative and productive use of Twitter to reach audiences and key influencers | Review Council's use of Twitter. Revise plan for submission to C&C subgroup. | Revise Twitter strategy and policy. Trial with SMT. | PH | SB
12 | G | 1. High | Support implementation | Digital capacity |  | Source alternative online consultation facility. | Brief Bang. | Work being taken forward by A&R team. | PH | SB
13 | G | 2. Medium | Reinforce reputation | Working with partners |  | Maintain constructive relationships with MoJ | Attend monthly Group Communication Board meeting. Inform MoJ News Planning of forthcoming activities. Ensure MoJ Press Office attend pre-launch "walk throughs". | PH re-arrange meeting with Emily Tofield, MoJ Dir of Comms. | PH/NM | MG
14 | G | 3. Low | Reinforce reputation | Working with partner orgs |  | Ensure stakeholder intelligence is managed well to support relationship building | Conduct stakeholder mapping exercise. Construct engagement grid for CEO. Embed use of stakeholder management tool within OSC | Review benefits for the organisation and current practice. | PH | MG
15 | O | 2. Medium | Promote confidence | Working with partner orgs |  | Ensure we meet our commitment to 20 activities/events in the 17/187 financial year. Promote use of OSC support for presentations. Promote new PowerPoint template. | 2016/17 Members of the Sentencing Council and OSC spoke at 28 events. Need to take a more strategic and active approach. | Research potential audiences/events. Approach key stakeholders with the offer of a speaker. Inform Council members re new PowerPoint template. | PH/NM | JulianG
16 | G | 2. Medium | Promote confidence | Expert advice |  | Proactive work with mainstream, legal and specialist media, and identifying other opportunities to promote confidence and demonstrate expertise | Respond to media requests for expertise. Pitch ideas for articles, features, blogs, programmes, contributions, etc. Identify potential opportunities in factual/fictional TV programming. | Draft policy for positioning Council as authority on sentencing. | NM
17 | G | 2. Medium | Promote confidence | Public and victims | Working with partners | Continued promotion of the victims materials - film, leaflets and tent cards - and info on website. | Evaluation of existing comms activities and exploration of future collaboration to be explored with WS. PH/NM met Head of Public Affairs, Victim Support 28/9. | To evaluate effectiveness of comms activity to meet objectives. Arrange meeting with WS. Enhance information about VPSs on website and assess if further information is required. | NM | MG
18 |  | 1. High | Promote confidence | Public and victims | Working with partners | Develop comms campaign to improve knowledge about sentencing among police officers | Draft research. Scope potential of likely activities. | Developing research proposal and specific comms plan with Simon B and Alex M. | NM | SB
19 | G | 3. Low | Reinforce reputation | Working with partners |  | Be alert to opportunities in Parliament. | Facilitiate meetings between Parliamentarians and Council Members. Brief the Chairman and other Council Members attending Justice Cttee meetings. | Monitor parliamentary activity, provide input to briefings for meetings and committee sessions | PH | JulianG
20 |  | 2. Medium | Promote confidence | Public and victims |  | Educational materials for schools | There is ongoing activity with the Citizenship Foundation to develop materials. Evaluation is also ongoing - there have been 2800 page views and 1500 unique visitors looking at the materials on the SC site, and 624 downloads from the TES site. Feedback has been requested from CF and the Assoc for Citizenship Teaching, but too early for evaluation from CF due to delays in SmartLaw website development. | Evaluate existing materials | NM | MG
21 | G | 3. Low | Promote confidence | Working with partners |  | Syndicate web-content on sentencing on partner websites. | Revised content now on CPS site with links to our site. Continue to review existing content on other partner sites including Open Justice (MoJ) and GOV.UK. Continue to press for "tile" on eJudiciary homepage. | Ongoing | NM | JillG
[6 empty] | 1. High | Digital capacity |  |  |  | JulianG | Support implementation
[6 empty] | 2. Medium | Publish guidelines and materials |  |  |  | JillG | Promote confidence
[6 empty] | 3. Low | Working with partners |  |  |  | SB | Reinforce reputation
[7 empty] | Public and victims |  |  |  | MG
[7 empty] | Expert advice |  |  |  | JulianG/JillG
JulianG/SB
JulianG/MG
JillG/SB
JillG/MG
SM/MG