## All activites
Action Log at December 2017
Line item | RAG rating | Priority /urgency | Strategic objective | Area | Area 2 | Action/comment | Comment/progress | Next action | Resp | Sub-grp sponsor
1 | G | 2. Medium | Support implementation | Publish guidelines and materials | Public and victims | via media: publicise release of draft and definitive guidelines and when guidelines come into force. | Ongoing work to nurture relationships with key journalists and identify specialist channels. | DGs: domestic abuse (Feb 18), knives, terrorism (Mar 18), breach (May 18); Consultations:public order (April18), arson (Mar 18), seriousness (May 18) | NM | JillG
2 | G | 2. Medium | Support implementation | Publish guidelines and materials | Working with partners | via practitioners: Maintain focus on implementation of guidelines. Issue summary briefing on new definitive guidelines for each agency and notification of coming into force. | All agencies receive and distribute articles via appropriate channels. |  | NM | JillG
3 |  | 2. Medium | Support implementation | Publish guidelines and materials |  | Manage design, production, print and digital publication of published materials. | All publications available in print and digital formats by publication date. |  | GS | JillG
4 |  | 2. Medium | Reinforce reputation | Publish guidelines and materials |  | Ensure effective launches of definitive guidelines, and appropriate participation in consultations | Design plan to evaluate launch and publicity activities, particularly impact on consultation responses | Format in place, will review after each guideline announcement. | PH/NM | MG
5 |  | 1. High | Support implementation | Digital capacity |  | Develop digital guidelines for Crown Court (CCSG) | Scope requirements. Draft project plan for agreement w SC SMT and C&C sub-grp. User research. Brief digital agency. | Circulate draft project plan. Contact Judge's Engagement Group and identify digital lead, if any. Engage with advisory group. Sit in on Crown Court proceedings. | PH | JulianG/JillG
6 |  | 2. Medium | Support implementation | Digital capacity |  | Create digital environment for successful implementation of CCSG | Key players in eJudiciary and other digital projects across CJS identified, demos seen. Press for "tile" and integrated content on eJudiciary. | Revisit eJudiciary re presentation and access via Bench Solution. | PH | JulianG/JillG
7 |  | 1. High | Support implementation | Digital capacity |  | Continue to refine MCSG in line with user feedback, and enhance functionality. | Ongoing programme of engagement with advisory group and improvements. | Contact group for advice on development of outstanding tools. | PH | JillG
8 |  | 1. High | Support implementation | Digital capacity |  | Develop Welsh-language MCSG | Welsh Language Unit engaged. Mirror website created. Council paper re assurance panel. | Identify, recuit and brief assurance panel | PH | JillG
9 | G | 1. High | Support implementation | Digital capacity |  | Refine and develop website - see separate entry for Members' area. | Build basic review requirements into new contract. Review content, language, structure. | Compile brief for reviewer. Put out to tender - closing date 3 Jan. | PH/GS | SB
10 | G | 3. Low | Support implementation | Digital capacity |  | Refine and develop Members' area of website, particularly tool for online collaboration on documents | Review requirements included in new contract. Survey Members. | Develop user research. Analyse existing and new user feedback to inform development. | PH/GS | JillG
11 |  | 2. Medium | Promote confidence | Digital capacity |  | Make creative and productive use of Twitter to reach audiences and key influencers | Review Council's use of Twitter. Revise plan for submission to C&C subgroup. | Revise Twitter strategy and policy. Trial with SMT. Identify influencers in CJS. | PH | SB
12 | G | 1. High | Support implementation | Digital capacity |  | Design programme of digital work for 2018 | Awaiting cost/resource assessments from Bang. | C&C group to consider prioritiies.
13 | G | 2. Medium | Reinforce reputation | Working with partners |  | Maintain constructive relationships with MoJ | Attend monthly Group Communication Board meeting. Inform MoJ News Planning of forthcoming activities. Ensure MoJ Press Office attend pre-launch "walk throughs". | Ongoing | PH/NM | MG
14 | G | 2. Medium | Reinforce reputation | Working with partner orgs |  | Ensure stakeholder intelligence is managed well to support relationship building | Conduct stakeholder mapping exercise. Construct engagement grid for CEO. Embed use of stakeholder management tool within OSC | Work with Emma Marshall, deputy CEO, to engage with priority stakeholders | PH | MG
15 | O | 2. Medium | Promote confidence | Working with partner orgs |  | Ensure we meet our commitment to 20 activities/events in the 17/187 financial year. Promote use of OSC support for presentations. Promote new PowerPoint template. | 2016/17 Members of the Sentencing Council and OSC spoke at 28 events. | Research potential audiences/events. Approach key stakeholders with the offer of a speaker. Inform Council members re new PowerPoint template. | PH/NM | JulianG
16 | O | 2. Medium | Promote confidence | Expert advice |  | Proactive work with mainstream, legal and specialist media, and identifying other opportunities to promote confidence and demonstrate expertise | Respond to media requests for expertise. Pitch ideas for articles, features, blogs, programmes, contributions, etc. | Draft policy for positioning Council as authority on sentencing. | NM
17 | G | 2. Medium | Promote confidence | Public and victims | Working with partners | Continued promotion of the victims materials - film, leaflets and tent cards - and info on website. | Evaluation of existing comms activities and exploration of future collaboration to be explored with WS. PH/NM met Head of Public Affairs, Victim Support 28/9. | Conduct evaluation of usage with WS, explore further usage, specifically London Mayor's victims' commissioner, court open days and magistrates in the community activities. | NM | MG
18 |  | 1. High | Promote confidence | Public and victims | Working with partners | Develop comms campaign to improve knowledge about sentencing among police officers | Strategy produced, actions being implemented | Activities planned with FLOs, Police Federation, Wecops. | NM | SB
19 | G | 3. Low | Reinforce reputation | Working with partners |  | Be alert to opportunities in Parliament. | Facilitiate meetings between Parliamentarians and Council Members. Brief the Chairman and other Council Members attending Justice Cttee meetings. | Monitor parliamentary activity, provide input to briefings for meetings and committee sessions. Brief Chairman for Justice Cttee session, Feb 2018. | PH | JulianG
20 |  | 2. Medium | Promote confidence | Public and victims |  | Educational materials for schools | Ongoing promotion to suitable channels e.g. MIC, have checked for accuracy sentencing scenarios and guideline materials produced by National Justice Museum for schools. | Evaluate existing materials, look for further channels for usage. | NM | MG
21 | G | 3. Low | Promote confidence | Working with partners |  | Syndicate web-content on sentencing on partner websites. | Revised content now on CPS site with links to our site. Continue to review existing content on other partner sites including Open Justice (MoJ) and GOV.UK. Continue to press for "tile" on eJudiciary homepage. | Ongoing | NM | JillG
[6 empty] | 1. High | Digital capacity |  |  |  | JulianG | Support implementation
[6 empty] | 2. Medium | Publish guidelines and materials |  |  |  | JillG | Promote confidence
[6 empty] | 3. Low | Working with partners |  |  |  | SB | Reinforce reputation
[7 empty] | Public and victims |  |  |  | MG
[7 empty] | Expert advice |  |  |  | JulianG/JillG
JulianG/SB
JulianG/MG
JillG/SB
JillG/MG
SM/MG